## Action Tracker
S.No | Task Category | Task Description | Owner | Status | Remarks
1 | General | Project folder in Github | Thiru | Completed
2 | Technology | Architecture draft finalization | Vasu/Thiru | In progress | JBoss
3 | Technology | First level Technology evaluation and finalization | Vasu/Thiru | In progress
4 | ETL | File format supported small ERP and other systems used by SMB | Thiru
5 | ETL | File transfer volume constraint analysis | Thiru
6 | Technology | Evaluate Rule Engine - Drool | Prem
7 | Solution Presentation | Market place | Prem | In progress | Market place slides
8 | Solution Presentation | Architecture | Thiru | In progress | Architecture
9 | Solution Presentation | Review | Ram
10 | Solution Presentation | Finalization | Vasu
11 | Approach Document | File Transfer | Prem |  | Use case flow
12 | Approach Document | ETL | Prem |  | End to end flow with details, Dashboard monitoring requirements
13 | Approach Document | Data Store | Thiru
14 | Approach Document | Analytic Model | Thiru
15 | Approach Document | Business Intelligence | Vasu/Prem
16 | Approach Document | Visualization | Vasu
17 | Approach Document | Customer Portal
18 | Approach Document | Subscription Module |  |  | Subscription and Usage monitoring
19 | Approach Document | App Store
20 | Approach Document | Ticketing Tool |  |  | Mantis?
21 | Approach Document | Community |  |  | Wordpress?
22 | Approach Document | Service Level Reports
23 | Approach Document | ETL Reports
24 | Approach Document | Overall Platform Technology/Design
25 | Approach Document | Security |  |  | LDAP, Single Sign on
26 | Approach Document | Trace/Track
27 | Approach Document | Metering/Usage |  |  | Xgvi
28 | Approach Document | Performance
29 | Approach Document | Monitoring
30 | Approach Document | Overall Platform Development/Maintenance
31 | Approach Document | Deployment
32 | Approach Document | Configuration
33 | Approach Document | API Manager
34 | Resources | Identify Java Resource | Thiru/Ram |  | Node.js and Angular.js
35 | Resources | Identify Infrastructure Resource | Vasu
36 | Business | Marketing Approach/Solution Positioning | Ram
37 | Business | Funding | Ram